## RiskWorkSheet
Risk Assessment Form
Group Name: | Biofeedback Device |  |  | Members: |  | Severity | Exposure | Probablity
|  |  |  | Chris Zhang |  | Catastrophic | Frequent | Probable
|  |  |  | Galen Cheng |  | Serious | Occasional | Possible
|  |  |  | Olivia Williams |  | Slight | Remote | Unlikely
[6 empty] | Minimal | None | Negligible
Item | User | Task | Hazard Category | Hazard | Cause/Failure Mode | Severity | Exposure | Probability | Risk Level | Method of Risk Reduction/Mitigation | Severity | Exposure | Probability | Risk Level | Person Responsible | Date | Comments
1a | All Users | Handle the device |  | Electrical | Moisture from hands or other object short circuits device | Serious | Remote | Unlikely | Medium | m | Minimal | Remote | Negligible | Low | Olivia Williams
1b | All Users | Handle the device |  | Heat/Temperature | Circuit overheats | Serious | Remote | Unlikely | Medium | Inform users in the manual to be cautious of circuit overheating | Minimal | Remote | Negligible | Low | Olivia Williams
2a | Patient | Place finger in device |  | Environmental/Industrial Hygene | Residue on finger prevents proper sensor utilization | Slight | Remote | Unlikely | Low | With user manual, remind patients to make sure hands are clean | Minimal | Remote | Negligible | Low | Olivia Williams
2b | Patient | Place finger in device |  | Electrical | Moisture from hands or other object short circuits device | Serious | Remote | Unlikely | Medium | With user manual, remind patients to make sure hands are dry | Minimal | Remote | Negligible | Low | Chris Zhang
2c | Patient | Place finger in device |  | Material Handling | Sensor detaches from moment arms | Serious | Remote | Unlikely | Low | Reinforce weaker areas near the attachment pieces | Slight | Remote | Unlikely | Medium | Galen Cheng
2d | Patient | Move finger within device |  | Material Handling | Overuse/overextension of device leads to diminished accuracy in sensor reading | Slight | Remote | Possible | Medium | Create interchangable backup attachments in case one scaffold fails | Minimal | Remote | Negligible | Low | Galen Cheng
2e | Patient | Callibrate each sensor |  | Eronomic/Human Factors | Cannot see distinguish messages on LED display | Minimal | None | Possible | Low | Remind patient to use device in well lit area | Minimal | None | Negligible | Low | Chris Zhang
2f | Patient | Callibrate each sensor |  | Eronomic/Human Factors | Cannot press buttons on interface because of small surface area | Minimal | None | Possible | Low | Remind patient to use properly working hand to utilize device | Minimal | None | Negligible | Low | Chris Zhang
2g | Patient | Callibrate each sensor |  | Material Handling | Moisture from hands or other object short circuits device | Serious | Remote | Unlikely | Medium | Remind patient to only use device when hands are dry | Minimal | Remote | Negligible | Low | Chris Zhang
3a | Occupation Therapist | Callibrate each sensor |  | Eronomic/Human Factors | Doesn't notice the miscalibration of the sensors | Slight | None | Possible | Low | Remind therapist to closely monitor patient utilization of device | Minimal | None | Negligible | Low | Chris Zhang
3b | Occupation Therapist | Assist patient with finger placement |  | Material Handling | Tightens device too tightly to the discomfort of the patient | Minimal | None | Possible | Low | Inform therapist to check-in with patient to assess comfort levels | Minimal | None | Negligible | Low | Olivia Williams
4a | Technician | Troubleshoot |  | Electrical | Over time, wires get crossed | Serious | None | Unlikely | Low | In users manual, suggest having electric tape on hand to prevent crossing | Minimal | None | Unlikely | Medium | Chris Zhang

## Lists
Severity | Exposure | Probability | Risk | Users | Hazard Category | Hazard
Catastrophic | Frequent | Probable | High | All Users | Biological/Health
Serious | Occasional | Possible | Medium | Doctor | Chemicals/Gases
Slight | Remote | Unlikely | Low | Fabricator | Electrical
Minimal | None | Negligible |  | Family | Environmental/Industrial Hygene
|  |  |  | Housekeeping | Eronomic/Human Factors
|  |  |  | Nurse | Fire/Explosion
|  |  |  | Nurse Aide | Fluid Pressure
|  |  |  | Occupation Therapist | Heat/Temperature
|  |  |  | Paramedic | Ingress/Egress
|  |  |  | Patient | Laser
|  |  |  | Public | Material Handling
|  |  |  | Service Technician | Mechanical
|  |  |  | Technician | Noise/Vibration
Radiation
Slip/Trip/Fall
Ventilation/Confined Space
Wastes